ASSIGNMENT : 6

1.How do you evaluate the performance of a project in agile?

   The key measures for evaluating agile project performance are:

Velocity
V=Units of efforts completed/ Sprint
        Velociy for first release plan is predicted which is created during project initiation after that actual velocity is measured at each timebox and this actual measure is used to predict the velocity for subsequent timeboxes in the release plan.
- Hit rate
Percentage of work allocated to a timebox that was actually completed.

Work remaining on tasks
Each day the remaining work is estimated on each task.

Project cost
It is estimated to make sure that the project is completed within the budget.

Three management measures are:
Cost performance index (CPI)
Cost Performance Index (CPI) = (Baseline Cost per Story Point)/(Actual Cost per Story Point)
CPI > 1 is an indication that cost incured for the project is less than what expected .
CPI<1 is an indication that the cost has exceeded the expected value.
CPI	=	EV/TAC
=	(BC/SP)/(AC/SP)

Schedule performance index (SPI)
Schedule Performance Index (SPI) = (Actual Velocity/Baseline Velocity)

SPI > 1 is an indication that the project has finished earlier than expected.
SPI < 1 is an indication that the project has finished late than expedcted.
SPI	=	EV/PV
=	AV/BV

Earned business value (EBV)
Earned value is defined as “the value of work completed”
EV=total story points times the baseline cost per story point

If project goes according to plan CPI and SPI would = 1 every Sprint
Based on the SPI and CPI values we can understand whether the project is going on time and on budget. Thus it helps determine the performance of a project.
2.Compare traditional monitoring & control with agile monitoring & control with respect to metrics generation.

Traditional Monitoring & Control	Agile Monitoring & Control
Business value is not determined	EBV is used to calculate business value
Monitoring and control will only occur in last phase of the project.	Monitoring and control will be happen in each sprint release.
Traditional project monitoring focuses on tracking how much effort is expended on each task	Agile provides more opportunities to monitor what is going on rather than how much is done
No burn down charts are created here.	Results are demonstrated using the burn down chart.
Variance from the plan is considered bad unless it is approved by Change Management.	Change is accepted and the change management is monitored well.
Traditional project management is very concerned about observing and measuring actual project performance against the plan and fixing it if it varies.	The best evidence that a software project is on track is working software, preferably deployed to production.
Communication can be of any form and does not restrict in any way.	Agile teams try to promote face-to-face communication and to reduce the channels of communication in general .
Not focused on colocation.	Colocation is done to ensure successful communication between the agile teams.
It is difficult to accurately estimate costs for any software development project. The actual performance of a project cannot be estimated easily	Technical performance, schedule and actual cost can be estimated by comparing the earned value (EV) with the planned value (PV)
Quality is measured in only one phase in the whole project life.	Quality is measured in each sprint life cylcle.
Risk matric is calculated for finding the open,closed risks associated with the project for the whole life.	Here risk will be checked for each sprint release.
Comparing plans is the measure of progress.	Emphasizing customer value and working software are the primary measure of progress.

3. With a total project budget of $ 175,000, and having completed one out of four iterations, we have this product backlog and these actuals:

Feature	Estimate / (storypoints)	Completed / (storypoints)	Actual Cost (1000s / dollars)
Welcome Screen	10	10	15
Advert - Splash Screen	20	20	30
Login Screen	10	10	20
Personalized Google Ads	20
Catalog Browser	20
Catalog Editor	10
Shopping Basket Browser	5
Shopping Card Editor	25
Check-out Process	20
Invoice Calculation	10
Credit Card Verification	10
PayPal Payment Handling	20
Order Confirmation Email	20
Totals	200	40	65

in our example, after Iteration 1 we should be at 25% complete)
- Calculate Planned Value
- Actual % Complete
- Earned Value
Answer:
Planned Value =(25/100) * 175,000 = $ 43,750
Actual % Complete= (40/200)*100= 20%
Earned Value= (20/100)*175,000= $35,000